## Sheet1
Done? | GF | Issue | Action | IG Location | Comment
| 20891 20899 | The Risk Management Plan is not tied to the Care Plan. | Add supportingInfo Reference(RiskAssessment_eltss) to the Differential Table AND Snapshot Table of the Care Plan Profile | Care Plan Profile: http://build.fhir.org/ig/HL7/eLTSS/CarePlan-eltss.html | the supportingInfo can be any resource, There's no way to hook it to RiskAssessement without breaking a lot of things.
| 20897 | The eLTSS mappings for Signatures are not included in the Contract Profile. Currently only the Person Signature is displayed. | Update Contract Profile Differential AND Snap Shot Tables to include the following: Contract.signer : Person, Guardian / Legal Representative, Support Planner, or Service Provider Signature Contract.signer.party: Person, Guardian / Legal Representative, Support Planner, or Service Provider Printed Name Contract.signer.signature.when: Person, Guardian / Legal Representative, Support Planner, or Service Provider Signature Date Contract.signer.signature.who: Person, Guardian / Legal Representative, Support Planner, or Service Provider Signature (This is currently mapped to Printed Name which is wrong) | Contract Profile: http://build.fhir.org/ig/HL7/eLTSS/Contract-eltss.html | Fixed
| 20892 | The Contract Profile still includes Device for a Support Planner Signature | Remove Device from the Support Planner Signature mappings. | http://build.fhir.org/ig/HL7/eLTSS/eLTSS_to_FHIR_R4_element.html | Fixed
| 20904 | There is still a typo in the ServicePlan Model | Fix the typo in the personSignature element: . personSignature 0..1 BackboneElement The of the person's signature as proof of identify and intent for the plan. | http://build.fhir.org/ig/HL7/eLTSS/eLTSSServicePlanModel.html | Fixed (a while ago, finally got the build to notice the change)
| 20992 | Why isn’t the statement regarding the Patient answered in the Resolution or Followup column of the reconciliation sheet or GForge? | Answer this statement: As well please confirm that the CapabilitiesStatement.rest element is populated correctly. It seems odd that the resource type would be "Patient" while the supported Profile references the eLTSS Careplan profile. | N/A | It is, what you're seeing is an artifact from the import of the USCore Capability Statement.
| N/A | Extension urls give 404 error | The following links give 404 errors - is this expected?: http://hl7.org/fhir/us/eLTSS/StructureDefinition/eltss-directedBy http://hl7.org/fhir/us/eLTSS/StructureDefinition/eltss-dueTo http://hl7.org/fhir/us/eLTSS/StructureDefinition/eltss-RiskPlan | http://build.fhir.org/ig/HL7/eLTSS/extension-eltss-directedBy.html http://build.fhir.org/ig/HL7/eLTSS/extension-eltss-dueTo.html http://build.fhir.org/ig/HL7/eLTSS/extension-eltss-RiskPlan.html | That's normal until the build is pushed to the FHIR main server
| 20891 | DocumentReference.contained information needs removed from Emergency Backup Plan mappings | Remove DocumentReference.contained information from Emergency Backup Plan mappings | http://build.fhir.org/ig/HL7/eLTSS/eLTSS_to_FHIR_R4_element.html | Done
|  |  | FINAL PUBLICATION: We need to include a link on the mappings page to the Gforge location where the XLS version of the mapping will reside. | http://build.fhir.org/ig/HL7/eLTSS/eLTSS_to_FHIR_R4_element.html | Uploaded, link updated